## Sheet1
User Stories And Accecptance Crieria
ID | As a | I want to | So that | Acceptance Criteria (format: use keywords Given, When, Then) | Status | Sprint
US 1 | Player/ Customer | control a tank with a keyboard | I can move around the battlefield and engage in combat with other tanks. | Scenario: Tank Movement Given: The player is on the game screen When: The player presses the arrow keys on the keyboard to control the tank's movement Then: The tank moves in the direction of the arrow key that was pressed. | Done | 1
US 2 | Player/ Customer | fire my tank's cannon | I can destroy enemies' tanks. | Scenario: Firing the Cannon Given: The player is on the game screen When: The player presses the spacebar on the keyboard to fire the cannon Then: The tank fires a shell in the direction it is facing. | Done | 1
US 3 | Player/ Customer | have a single-player mode | I can practice my skills and strategies against AI-controlled tanks. | Scenario: Single-player mode Given: The player is on the game screen When: The player selects the Game Start option Then: The game starts in single-player mode, with AI-controlled tanks as enemies and allies. | Done | 1
US 4 | Player/ Customer | have a variety of maps to choose from | I can experience different terrains and battlefields. | Scenario: Choosing a Map Given: The player is on the game screen When: The player selects the map selection option Then: A list of available maps is displayed, and the player can select one to start the game on that map. | Done | 2
US 5 | Player/ Customer | have enemies and allies | I can experince different situtations and have more fun | Scenario: Enemies and Allies Given: The player is on the game screen When: The game starts Then: Enemies and allies are present on the battlefield, and the player can differentiate between them. | Done | 1
US 6 | Player/ Customer | have a scoreboard that shows my score | I can see how many score I get. | Scenario: Scoreboard Given: The player is on the game screen When: The game is in progress Then: The scoreboard displays the player's score | Done | 1
US 7 | Player/ Customer | have multiple lives | I'm not gonna let one mistake end the game | Scenario: Multiple Lives Given: The game is in progress When: The player's tank takes damage Then: The tank loses a life, and the player can continue playing with the remaining lives. | Done | 1
US 8 | Player/ Customer | have different language options | fit my language preferences. | Scenario: Language Options Given: The player is on the game screen When: The language selection option is available Then: The player can select a language preference, and the game's language will be changed accordingly. | Done | 2
US 9 | Player/ Customer | pause the game at any time | take a break or attend to other matters. | Scenario: Pausing the Game Given: The game is in progress When: The player presses the pause button Then: The game is paused, and the player can resume playing or exit the game. | Done | 2
US 10 | Player/ Customer | play on different difficulty levels | I can challenge myself and get different experiences. | Scenario: Difficulty Levels Given: The player is on the game screen When: The player selects a difficulty level Then: The game's difficulty is changed, and the player experiences a different level of challenge. | Done | 2
US 11 | Player/ Customer | my shells to score differently when they hit enemy forces | affecting my strategy and scoring. | Scenario: Shell Scoring Given: The player's tank fires a shell When: The shell hits an enemy tank Then: The player scores points. If the shell hits a friendly tank, the player loses points. | Done | 2
US 12 | Player/ Customer | have different kind of enemies | enrich my game experience | Scenario: Different Types of Enemies Given: The game is in progress When: The player encounters different types of enemy tanks Then: The player experiences a variety of gameplay challenges. | Done | 1
US 13 | Player/ Customer | customize my game's graphics, such as resolution and quality | I can get the best game experience | Scenario: Graphics Customization Given: The player is on the game screen When: The graphics customization option is available Then: The player can adjust the game's graphics settings, such as resolution and quality. | Not Done | 2
US 14 | Player/ Customer | collect power-ups such as health boosts, speed boosts | I can increase my chances of survival and progress through the game. | Scenario: Power-Ups Given: The player is on the game screen When: The player collects a power-up Then: The player's tank gains a benefit, such as increased health or speed. | Done | 2
US 15 | Player/ Customer | see the lives status of my tank | I can know how much damage I can sustain | Scenario: Lives Status Given: The game is in progress When: The player's tank takes damage Then: The lives status of the tank is updated to reflect the remaining health. | Done | 1
US 16 | Player/ Customer | be able to hide behind obstacles such as walls and rocks | I can avoid enemy fire and ambush them. | Scenario: Obstacle Hiding Given: The player's tank is near an obstacle, such as a wall or rock When: The player presses the hide button Then: The tank moves behind the obstacle and is hidden from enemy fire. | Done | 2
US 17 | Player/ Customer | be able to customize my tank's appearance with different skins and colors | I can personalize my gameplay experience. | Scenario: Tank Skin Customization Given: The user is on the main menu When: The user selects the "customize tank" option Then: The system displays the customization options, including skins and colors And: The user can select a skin and color And: The system applies the selected skin and color to the tank | Done | 2
US 18 | Player/ Customer | have access to different types of tanks with different stats, such as speed, health, and firepower | I can choose the one that suits my playstyle the best | Access to Different Types of Tanks Scenario: Tank Selection Given: The user is on the main menu When: The user selects the "choose tank" option Then: The system displays the tank options, including their stats such as speed, health, and firepower And: The user can select a tank that suits their playstyle the best And: The system applies the selected tank and its stats to the gameplay | Done | 2
US 19 | Player/ Customer | want enemies and friends to respawn constantly | I can constantly encounter new situations to enrich my experience | Scenario: Enemy respawn Given: The player starts a game When: The player destroys an enemy tank Then: A new enemy tank immediately appears on the battlefield When: The player's ally tank is destroyed Then: A new ally tank immediately appears on the battlefield | Done | 1
US 20 | Player/ Customer | have access to different sound effects for different actions, such as firing a cannon or collecting a power-up | enrich my game experience | Scenario: Sound Effect Customization Given: The user is on the main menu When: The user selects the "sound options" option Then: The system displays the sound options, including different sound effects for different actions And: The user can select a sound effect for each action And: The system applies the selected sound effects to the gameplay | Done | 2