## Sheet1
User Stories
ID | As a | I want to | So that | Status | Sprint
US 1 | Player/ Customer | control a tank with a keyboard | I can move around the battlefield and engage in combat with other tanks. | Done | 1
US 2 | Player/ Customer | fire my tank's cannon | I can destroy enemies' tanks. | Done | 1
US 3 | Player/ Customer | have a single-player mode | I can practice my skills and strategies against AI-controlled tanks. | Done | 1
US 4 | Player/ Customer | have a variety of maps to choose from | I can experience different terrains and battlefields. | To be Done
US 5 | Player/ Customer | have enemies and allies | I can experince different situtations and have more fun | Done | 1
US 6 | Player/ Customer | have a scoreboard that shows my score | I can see how many score I get. | Done | 1
US 7 | Player/ Customer | have multiple lives | I'm not gonna let one mistake end the game | Done | 1
US 8 | Player/ Customer | have different language options | fit my language preferences. | To be Done
US 9 | Player/ Customer | pause the game at any time | take a break or attend to other matters. | To be Done
US 10 | Player/ Customer | play on different difficulty levels | I can challenge myself and get different experiences. | To be Done
US 11 | Player/ Customer | my shells to score differently when they hit friendly and enemy forces | affecting my strategy and scoring. | Done | 1
US 12 | Player/ Customer | have different kind of enemies | enrich my game experience | Done | 1
US 13 | Player/ Customer | customize my game's graphics, such as resolution and quality | I can get the best game experience | To be Done
US 14 | Player/ Customer | collect power-ups such as health boosts, speed boosts | I can increase my chances of survival and progress through the game. | To be Done
US 15 | Player/ Customer | see the lives status of my tank | I can know how much damage I can sustain | Done | 1
US 16 | Player/ Customer | be able to hide behind obstacles such as walls and rocks | I can avoid enemy fire and ambush them. | To be Done
US 17 | Player/ Customer | be able to customize my tank's appearance with different skins and colors | I can personalize my gameplay experience. | To be Done
US 18 | Player/ Customer | have access to different types of tanks with different stats, such as speed, health, and firepower | I can choose the one that suits my playstyle the best | To be Done
US 19 | Player/ Customer | want enemies and friends to respawn constantly | I can constantly encounter new situations to enrich my experience | Done | 1
US 20 | Player/ Customer | have access to different sound effects for different actions, such as firing a cannon or collecting a power-up | enrich my game experience | To be Done